## QF-QCM (1)
A03_QF-QCM-V4 Internal Quality Control and Monitoring (v4)
Responsible: Tom SAVU |  |  |  |  | Evaluation period: 01.10.2017 – 31.12.2018 |  |  |  |  | Completion date: 25.01.2019
According to MSIE4.0-Project-Management-and-Communication-Plan-PMCP-V1.1.pdf
Work Package | Task | Deliverables |  | Planned Start date | Planned End date | Actual Start date | Actual End date |  |  | Task leader | Indicator(s) | Results | Status | Observations, suggestions
[7 empty] | WP | QCMB | PEC
WP1 | T1.1 | O1.1 | Gap Analysis working plan | 2018-01-01 | 2018-03-31 |  | 2018-05-31 | 2018-11-22 | 2018-06-11 | Wichai Chattinnawat, Rui Lima | QF-ECI-T1.1 | REVISED-WORKING-PLAN-WP1-approved-by-PEC.pdf | TO BE REDRAFTED | Dates from WP1 Leader and from QCMB do not match
WP1 | T1.2 | O1.2 | Comprehensive analysis of MSIE curricula in Thailand and in EU partner countries | 2018-03-01 | 2018-07-31 |  | 2018-12-29 | 2018-11-12 | 2018-12-27 | Rui Lima | QF-ECI-T1.2 | GD-T1.2_O1.2 (V6).docx | DONE-FINAL | Some dates from WP1 Leader and from QCMB do not match
|  | O1.3 | Assessment of learning and teaching tools and methods in Thailand and in EU partner countries |  |  |  | 2018-12-30 | 2018-11-13 |  | Rui Lima |  | GD-T1.2_O1.3 (V5).docx | Wating PEC approval | Some dates from WP1 Leader and from QCMB do not match
WP1 | T1.3 | O1.4 | Analysis of needs of industry and students | 2018-04-01 | 2018-09-30 |  |  |  |  | Rui Lima | QF-ECI-T1.3 |  | OPEN-DRAFT
WP1 | T1.4 | O1.5 | Gaps between the needs and graduates’ competences | 2018-08-01 | 2018-09-30 |  |  |  |  | Rui Lima | QF-ECI-T1.4 |  | OPEN-DRAFT
WP1 | T1.5 | O1.6 | Competitive factors for the curriculum | 2018-08-01 | 2018-09-30 |  |  |  |  | Rui Lima | QF-ECI-T1.5 |  | OPEN-DRAFT
WP1 | T1.6 | O1.7 | Recommendations for specifications and areas of specialization for the curriculum | 2018-09-01 | 2018-10-31 |  |  |  |  | Rui Lima | QF-ECI-T1.6 |  | OPEN-DRAFT
WP2 | T2.1 | O2.1 | A modernized curriculum for Master’s degree in IE | 2018-12-01 | 2018-12-31 |  |  |  |  | Tomasz Nitkiewicz | QF-ECI-T2.1 |  | NOT YET STARTED
WP2 | T2.2 | O2.2 | Syllabuses for all courses in the curriculum | 2018-12-01 | 2019-04-30 |  |  |  |  | Tomasz Nitkiewicz | QF-ECI-T2.2 |  | NOT YET STARTED
WP3 | T3.1 | O3.1 | Teaching materials for instructors | 2018-12-01 | 2019-11-30 |  |  |  |  | Diana Mesquita |  |  | NOT YET STARTED
WP3 | T3.3 | O3.3 | A platform for online learning | 2018-04-01 | 2018-09-30 | 2018-04-01 |  |  |  | Mongkol Ekpanyapong | QF-ECI-T3.3 |  | Developed and tested with one course at AIT. | User guide to be completed and distributed
WP3 | T3.4 | O3.4 | Trained instructors and staffs on new teaching tools and methods. Three workshop | 2018-02-01 | 2018-02-28 |  |  |  |  | Rui Lima
|  |  |  | 2018-09-01 | 2018-09-30 | [8 empty] | A training sessions took place during the meeting in Portugal
WP5 | T5.1 | O5.1 | Dissemination, Exploitation and Sustainable Plan | 2018-01-01 | 2018-03-31 | 2018-03-01 | 2019-01-17 | 2018-10-01 |  | Andrei DUMITRESCU | QF-ECI-T5.1 | DESP(V0.8) | OPEN-DRAFT | The plan must be submitted by WP5 Leader or CoLeader to PEC for aproval
WP5 | T5.2 | O5.2 | Project website | 2018-01-01 | 2020-09-30 | [5 empty] | QF-ECI-T5.2 | Website functional QF-WEB-V2 Website questionnaire report | On-going | The evaluation involved the users feedbacks (questionnaires)
WP5 | T5.3 | O5.3 | Dissemination materials | 2018-03-01 | 2018-04-30 |  |  |  |  | Thitipong Jamrus |  |  |  | No data
WP5 |  |  |  | 2018-09-01 | 2018-10-31 | [8 empty] | No data
WP5 | T5.6 | O5.6 | Dissemination events organized | 2018-09-01 | 2018-09-30 |  |  |  |  | Wichai Chattinnawat |  |  |  | No data