## QF-QCM (2)
A03_QF-QCM-V4 Internal Quality Control and Monitoring (v4)
Responsible: Tom SAVU |  |  |  |  | Evaluation period: 01.01.2019 – 28.02.2019 |  |  |  |  | Completion date: 25.03.2019
According to MSIE4.0-Project-Management-and-Communication-Plan-PMCP-V1.1.pdf
Work Package | Task | Deliverables |  | Planned Start date | Planned End date | Actual Start date | Actual End date |  |  | Task leader | Indicator(s) | Results | Status | Observations, suggestions
[7 empty] | WP | QCMB | PEC
WP1 | T1.1 | O1.1 | Gap Analysis working plan | 2018-01-01 | 2018-03-31 | 2018-01-01 | 2018-05-31 | 2018-11-22 | 2018-06-11 | Wichai Chattinnawat, Rui Lima | QF-ECI-T1.1 | REVISED-WORKING-PLAN-WP1-approved-by-PEC.pdf | REDRAFTED | Dates from WP1 Leader and from QCMB do not match. In this case, the QCMP and PMCP procedure were not respected. The report was sent first to PEC. The issue did not repeated with the next outcomes.
[12 empty] | GD-T1.1_O1.1 (V3) | DONE-FINAL
WP1 | T1.2 | O1.2 | Comprehensive analysis of MSIE curricula in Thailand and in EU partner countries | 2018-03-01 | 2018-07-31 | 2018-03-14 | 2018-12-29 | 2018-11-12 | 2018-12-27 | Rui Lima | QF-ECI-T1.2 | GD-T1.2_O1.2 (V6).docx | DONE-FINAL
|  | O1.3 | Assessment of learning and teaching tools and methods in Thailand and in EU partner countries |  |  |  | 2018-12-30 | 2018-11-13 | 2019-01-11 | Rui Lima |  | GD-T1.2_O1.3 (V5).docx | DONE-FINAL
WP1 | T1.3 | O1.4 | Analysis of needs of industry and students | 2018-04-01 | 2018-09-30 | 2018-05-15 | 2019-01-05 | 2019-01-14 | 2019-01-24 | Rui Lima | QF-ECI-T1.3 | GD-T1.3_O1.4 (V7).docx | DONE-FINAL
WP1 | T1.4 | O1.5 | Gaps between the needs and graduates’ competences | 2018-08-01 | 2018-09-30 | 2018-09-15 | 2019-01-17 | 2019-01-24 | 2019-02-05 | Rui Lima | QF-ECI-T1.4 | GD-T1.4_O1.5 (V4).docx | DONE-FINAL
WP1 | T1.5 | O1.6 | Competitive factors for the curriculum | 2018-08-01 | 2018-09-30 | 2018-10-15 | 2019-02-06 | 2019-02-14 | 2019-02-22 | Rui Lima | QF-ECI-T1.5 | GD-T1.5_O1.6 (V4).docx | DONE-FINAL
WP1 | T1.6 | O1.7 | Recommendations for specifications and areas of specialization for the curriculum | 2018-09-01 | 2018-10-31 | 2018-11-15 | 2019-02-24 | 2019-03-06 | 2019-03-13 | Rui Lima | QF-ECI-T1.6 | GD-T1.6_O1.7 (V2).docx | DONE-FINAL
WP2 | T2.1 | O2.1 | A modernized curriculum for Master’s degree in IE | 2018-12-01 | 2018-12-31 | 2019-01-29 |  |  |  | Tomasz Nitkiewicz | QF-ECI-T2.1 |  | OPEN-DRAFT | Estimated end date: April 2019
WP2 | T2.2 | O2.2 | Syllabuses for all courses in the curriculum | 2018-12-01 | 2019-04-30 | 2019-01-30 |  |  |  | Tomasz Nitkiewicz | QF-ECI-T2.2 |  | OPEN-DRAFT
WP2 | T2.3 | O2.3 | Pilot teaching in modernized MSc at partner universities | 2019-02-02 | 2019-06-30 |  |  |  |  | Huynh Trung Luong | QF-ECI-T2.3 |  | NOT YET STARTED
WP3 | T3.1 | O3.1 | Teaching materials for instructors | 2018-12-01 | 2019-11-30 |  |  |  |  | Diana Mesquita |  |  | NOT YET STARTED
WP3 | T3.2 | O3.2 | Learning materials for students | 2019-01-01 | 2020-01-31 |  |  |  |  | Montalee Sasananan |  |  | NOT YET STARTED
WP3 | T3.3 | O3.3 | A platform for online learning | 2018-04-01 | 2018-09-30 |  |  |  |  | Mongkol Ekpanyapong | QF-ECI-T3.3 |  | OPEN-DRAFT | The detailed user guide will be developed later when we install a new server for the platform in which Webrtc will be used instead of Java so that online lectures can be run. This change needs to be done because Java is not supported by all browsers since November, 2018.
WP3 | T3.4 | O3.4 | Trained instructors and staffs on new teaching tools and methods. Three workshop | 2018-02-01 | 2018-02-28 |  |  |  |  | Rui Lima |  |  | NOT YET STARTED
|  |  |  | 2018-09-01 | 2018-09-30 | [7 empty] | NOT YET STARTED | A training sessions took place during the meeting in Portugal
WP3 | T3.5 | O3.5 | Online learning materials | 2019-03-01 | 2020-01-21 |  |  |  |  | Mongkol Ekpanyapong |  |  | AWAITING START
WP3 | T3.6 | O3.6 | Installed hardware and software | 2019-01-01 | 2019-09-30 |  |  |  |  | A.M. Harsha S. Abeykoon |  |  | NOT YET STARTED
WP5 | T5.1 | O5.1 | Dissemination, Exploitation and Sustainable Plan | 2018-01-01 | 2018-03-31 | 2018-03-01 | 2019-01-17 | 2018-10-01 |  | Andrei DUMITRESCU | QF-ECI-T5.1 | DESP(V0.8) | TO BE SUBMITTED TO PEC | The plan must be submitted by WP5 Leader or CoLeader to PEC for aproval
WP5 | T5.2 | O5.2 | Project website | 2018-01-01 | 2020-09-30 | 2018-01-12 |  |  |  |  | QF-ECI-T5.2 | Website functional QF-WEB-V2 Website questionnaire report | ONGOING | The evaluation involved the users feedbacks (questionnaires)
WP5 | T5.3 | O5.3 | Dissemination materials | 2018-03-01 | 2018-04-30 | 2018-03-30 |  |  |  | Thitipong Jamrus |  |  | ONGOING
WP5 |  |  |  | 2018-09-01 | 2018-10-31 | 2018-09-01 | [6 empty] | ONGOING
WP5 | T5.4 | O5.4 | Publications in professional journals, newspapers, magazines, brochures and social media | 2019-02-01 | 2019-03-31 | 2019-02-01 |  |  |  | Rui Lima |  |  | ONGOING
WP5 | T5.6 | O5.6 | Dissemination events organized | 2018-09-01 | 2018-09-30 | 2018-09-19 |  |  |  | Wichai Chattinnawat |  |  | ONGOING