## QF-QCM 31.10.20
A03_QF-QCM-V4 Internal Quality Control and Monitoring 12
Responsible: Tom SAVU |  |  |  |  | Evaluation period: 01.09.2020 – 31.10.2020
According to MSIE4.0-Project-Management-and-Communication-Plan-PMCP-V1.1.pdf for WP1 and PMCP-V2.0/12.04.2019 for the rest of WPs
Work Package | Task | Deliverables |  | Planned Start date | Planned End date | Actual Start date | Actual End date |  |  | Task leader | Indicator(s) | Results | Status | Observations, suggestions
[7 empty] | WP | QCMB | PEC
WP1 | T1.1 | O1.1 | Gap Analysis working plan | 2018-01-01 | 2018-03-31 |  | 2018-05-31 | 2018-11-22 | 2018-06-11 | Wichai Chattinnawat, Rui Lima | QF-ECI-T1.1 | REVISED-WORKING-PLAN-WP1-approved-by-PEC.pdf | REDRAFTED | Dates from WP1 Leader and from QCMB do not match
[7 empty] | 2019-01-15 |  |  |  |  | GD-T1.1_O1.1 (V1) | DONE-FINAL
WP1 | T1.2 | O1.2 | Comprehensive analysis of MSIE curricula in Thailand and in EU partner countries | 2018-03-01 | 2018-07-31 |  | 2018-12-29 | 2018-11-12 | 2018-12-30 | Rui Lima | QF-ECI-T1.2 | GD-T1.2_O1.2 (V6).docx | DONE-FINAL | Some dates from WP1 Leader and from QCMB do not match
|  | O1.3 | Assessment of learning and teaching tools and methods in Thailand and in EU partner countries |  |  |  | 2018-12-30 | 2018-11-13 | 2019-01-11 | Rui Lima |  | GD-T1.2_O1.3 (V5).docx | DONE-FINAL | Some dates from WP1 Leader and from QCMB do not match
WP1 | T1.3 | O1.4 | Analysis of needs of industry and students | 2018-04-01 | 2018-09-30 |  | 2019-01-05 | 2019-01-14 | 2019-01-24 | Rui Lima | QF-ECI-T1.3 | GD-T1.3_O1.4 (V6).docx | DONE-FINAL
WP1 | T1.4 | O1.5 | Gaps between the needs and graduates’ competences | 2018-08-01 | 2018-09-30 |  | 2019-01-17 | 2019-01-24 | 2019-02-05 | Rui Lima | QF-ECI-T1.4 | GD-T1.4_O1.5 (V4).docx | DONE-FINAL
WP1 | T1.5 | O1.6 | Competitive factors for the curriculum | 2018-08-01 | 2018-09-30 |  | 2019-02-06 | 2019-02-14 | 2019-02-22 | Rui Lima | QF-ECI-T1.5 | GD-T1.5_O1.6 (V4).docx | DONE-FINAL
WP1 | T1.6 | O1.7 | Recommendations for specifications and areas of specialization for the curriculum | 2018-09-01 | 2018-10-31 |  | 2019-02-24 | 2019-03-06 | 2019-03-13 | Rui Lima | QF-ECI-T1.6 | GD-T1.6_O1.7 (V2).docx | DONE-FINAL
WP2 | T2.1 | O2.1 | A modernized curriculum for Master’s degree in IE | 2019-01-01 | 2019-03-31 | 2019-01-29 | 2020-02-11 | 2020-03-04 | 2020-05-14 | Robert ULEWICZ | QF-ECI-T2.1 |  | DONE-FINAL
WP2 | T2.2 | O2.2 | Syllabuses for all courses in the curriculum | 2019-02-01 | 2019-06-30 | 2019-01-30 | 2020-07-16 | 2020-08-13 | 2020-09-21 | Robert ULEWICZ | QF-ECI-T2.2 |  | DONE-FINAL
WP2 | T2.3 | O2.3 | Pilot teaching in modernized MSc at partner universities | 2019-08-01 | 2020-05-31 | 2019-08-08 | 2020-05-27 |  |  | Huynh Trung Luong |  |  | WAITING QCMB APPROVAL
WP2 | T2.4 | Q2.4 | Assessment of pilot test of the key courses and improved courses | 2020-05-01 | 2020-05-31 |  | 2020-10-13 | 2020-10-15 | 2020-10-19 |  |  |  | DONE-FINAL
WP2 | T2.5 |  | Preparation for accreditation of the curriculum | 2019-11-01 | 2020-05-31 |  |  |  |  | Kanchana Sethanan |  |  | OPEN-DRAFT?
WP3 | T3.1 | O3.1 | Teaching materials for instructors | 2019-05-01 | 2020-04-30 | 2019-08-01 | 2020-10-14 |  |  | Diana Mesquita |  |  | ONGOING
WP3 | T3.2 | O3.2 | Learning materials for students | 2019-06-01 | 2020-06-30 |  |  |  |  | Montalee Sasananan |  |  | ONGOING | Expected to start in January 2020
WP3 | T3.3 | O3.3 | A platform for online learning | 2018-04-01 | 2019-01-31 | 2018-04-01 | 2019-02-25 | 2020-10-23 |  | Mongkol Ekpanyapong |  |  | WAITING PEC APPROVAL
WP3 | T3.4 | O3.4 | Trained instructors and staffs on new teaching tools and methods. | 2018-02-01 | 2018-02-28 | 2018-02-13 | 2019-02-15 | 2020-10-19 |  | Rui Lima |  |  | WAITING PEC APPROVAL
|  |  |  | 2018-09-01 | 2018-09-30 | 2018-09-12 | 2018-09-15 | [5 empty] | ONGOING | Waiting for the organisers report.
|  |  |  | 2019-01-01 | 2019-01-31 | 2019-01-28 | 2019-01-29 | [5 empty] | OPEN-DRAFT
|  |  |  | 2019-06-01 | 2019-06-30 | 2019-06-06 | 2019-06-08 | [5 empty] | ONGOING | Waiting for the organisers report.
WP3 | T3.5 | O3.5 | Online learning materials | 2019-07-01 | 2020-05-31 | [7 empty] | ONGOING
WP3 | T3.6 | O3.6 | Installed hardware and software | 2019-01-01 | 2019-09-30 |  |  |  |  | A.M. Harsha S. Abeykoon |  |  | OPEN-DRAFT
WP3 | T3.7 | O3.7 | Laboratory equipped with online remote access from partner locations | 2019-10-01 | 2020-03-31 | 2019-02-18 |  |  |  | A.M. Harsha S. Abeykoon |  |  | ONGOING
WP5 | T5.1 | O5.1 | Dissemination, Exploitation and Sustainable Plan | 2018-01-01 | 2018-03-31 | 2018-03-01 | 2019-01-17 | 2018-10-01 | 2019-06-25 | Andrei DUMITRESCU |  |  | DONE-FINAL | Some dates from WP1 Leader and from QCMB do not match
WP5 | T5.2 | O5.2 | Project website | 2018-01-01 | 2020-09-30 | 2018-02-12 | [6 empty] | ONGOING
WP5 | T5.3 | O5.3 | Dissemination materials | 2018-03-01 | 2018-04-30 | 2018-03-30 |  |  |  | Thitipong Jamrus |  |  | ONGOING
|  |  |  | 2018-09-01 | 2018-10-31 | 2018-09-01 | [6 empty] | ONGOING
|  |  |  | 2019-03-01 | 2019-04-30
|  |  |  | 2019-09-01 | 2019-10-31
WP5 | T5.4 | O5.4 | Publications in professional journals, newspapers, magazines, brochures and social media | 2019-02-01 | 2019-03-31 | 2019-02-01 |  |  |  | Rui Lima |  |  | ONGOING
|  |  |  | 2019-08-01 | 2019-09-30
WP5 | T5.5 | O5.5 | Short-term courses in the field of Industrial Engineering for professionals | 2019-10-01 |  | Not yet started
WP5 | T5.6 | O5.6 | Dissemination events organized | 2018-09-01 | 2018-09-30 | 2018-09-19 |  |  |  | Wichai Chattinnawat |  |  | ONGOING
|  |  |  | 2019-03-01 | 2019-03-31 | [7 empty] | ONGOING
|  |  |  | 2019-09-01 | 2019-09-30 | [7 empty] | ONGOING
Note on H27: Message sent not only to the team
Note on H29: Didn't receive the team report sent to QCMB
Note on H30: Didn't receive the team report sent to QCMB