## Slide 1: WP4 – Action Plan
Livia LAZAR

## Slide 2: Task 4.3 -Inviting external evaluation of the project results FINAL REPORT
Table 2. Evaluation criteria identification responsible
.
Main responsible: Task 4.3 Leader – Supapan Chaiprapat
- with the support of all the project members
Action | Start time | End time
Carrying out actions to contract the auditor | A.S.A.P. | February 28th, 2020
Assuring support for the auditor on performing the audit process (*) if possible for the auditor to be present during the final dissemination-sustainability conference | August 28th, 2020 (or sooner) | September 4th, 2020
Assuring the communication between QCMB, PEC and auditor in the approving process of the final report. | September 4th, 2020 | September 25th, 2020
Communicate with QCMB, PEC and involved parties in order to ensure the correct establishment of the necessary actions and their implementation (if there is needed according to the auditor’s observations) | From the moment that the auditor mentioned in the audit process | October 9th, 2020

## Slide 3: Task 4.4 -Inviting external financial audit Main responsible: Task 4.4 Leader – Supapan Chaiprapat - with the support of all the project members, especially the administrative part
Table 2. Evaluation criteria identification responsible
.
Action | Start time | End time
Propose for selection the potential candidates | Already started | Feb. 28th, 2020
QCMB auditor’s selection (main criteria: experience, availability, budget) | Feb. 28th, 2020 | Mar. 3rd, 2020
PEC auditor’s approval | Mar. 3rd, 2020 | Mar. 6rd, 2020
Carrying out actions to contract the auditor | Mar. 6rd, 2020 | Mar. 31rd, 2020
Assuring support for the auditor on performing the audit process (with submitting the report) First stage for period 15.10.2017 - audit date Final stage for remaining period | April 20th, 2020 Sep. 28th, 2020 | April 30th, 2020 Oct. 9th, 2020
Assuring the communication between QCMB, PEC and auditor in the approving process of the report. |  | Within 3 days from report submitting
Communicate with PEC and involved parties in order to ensure the correct establishment of the necessary actions and their implementation (if there is needed according to the auditor’s observations) | From the moment that the auditor mentioned in the audit process | No later then October 14th, 2020